## spaghetti_task
Label | Tasks | Start Time | Duration | End Time
A | Chop ingredients (onion, celery, tomato, garlic…) | 19:00 | 0:15 | 19:15
B | Fry onions and celery | 19:15 | 0:10 | 19:25
C | Fry garlic and tomatoes | 19:25 | 0:02 | 19:27
D | Add chopped tomatoes | 19:27 | 0:01 | 19:28
E | Simmer | 19:28 | 0:30 | 19:58
F | Salt water | 19:40 | 0:01 | 19:41
G | Boil water | 19:41 | 0:06 | 19:47
H | Cook spaghetti | 19:47 | 0:11 | 19:58
I | Serve! | 19:58 | 0:02 | 20:00

## paper_writing_timeline
Tasks | Start Day | Duration | End Day
Read papers on similar work | 2024-01-01 | 2 | 2024-01-03
Draft lit review | 2024-01-03 | 2 | 2024-01-05
Draft methods section | 2024-01-05 | 1 | 2024-01-06
Draft results section (writing) | 2024-01-06 | 1 | 2024-01-07
Create figures for report | 2024-01-07 | 2 | 2024-01-09
Write discussion | 2024-01-09 | 1 | 2024-01-10
Proofread and list edits/corrections | 2024-01-10 | 1 | 2024-01-11
Action edits/corrections | 2024-01-11 | 3 | 2024-01-14
Write abstract, conclusion, and introduction | 2024-01-14 | 1 | 2024-01-15
Formulas:
End Day = [Start Day]+[Duration]